## Sheet1
Task	Who	Duration	When
			05/26/20	05/27/20	05/28/20	05/29/20	05/30/20	05/31/20	06/01/20
Daily
Meet with Pokemon marketing team to ensure we’re all on same page and right track		1 hour
Social media posting
Check in with engineering team

Day 1
Finalize plan with Pokemon team		1 hour
Choose 10 Pokemon for contest		1 hour
Send concept for @jinapup to designer and solicit design		10 minutes
Seek out voiceover talent and agree quotes for 2 minute voiceover		2 hours
Agree quotes from video producer, graphic designer and confirmation they can complete tasks in time		1 hour
Write video script for 2 minute video and send to producer, voiceover		1 hour
Present website plan to engineering team		30 minutes
Create social media accounts		1 hour
Set up dedicated email address for enquiries		10 minutes

Day 2
Engineering team build challenge website		3 days
Engineering team train and test model		3 days
Write and upload announcement to $COMPANY website		1 hour
Promote announcement via social media and other channels (our own and paid)		1 hour
Check progress with creative teams (video, graphics, etc)		2 hours
Receive Jinapup design and give feedback		1 hour
Receive final Jinapup design and send to video producer		1 hour
Pokemon make announcement via their channels		2 hours
Field Q+A from press and public		Ongoing
Receive and give feedback on voiceover		1 hour

Day 3
Receive final voiceover and send to video editor		1 hour
Receive and give feedback on video visuals		1 hour
Video producer makes edits and adds voiceover(s)		4 hours
Receive final video, upload to channels		2 hours
Check in with engineering team, share visuals (e.g. Jinapup)		1-2 hours